## Group Contribution Log
Course | CS3343
Term | 2017-18 Semester A
Project No. | 14
Project Name/Title | Maverick - The Smart Trading Platform
No. of Team Members | 5
Project Manager Name | Dheeraj Khurana
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | If Group Mark is: | Final Adjusted
54227224 | Khurana, Dheeraj | 2 | 4 | 5 | 5 | 3 | 3 | 3 | 3 | 4 | 6 | 5 | 3 | 4 | 50 | Khurana, Dheeraj | 1 | 100% | 80 | 80
54395023 | Singh, Navwinder | 2 | 3 | 3 | 6 | 4 | 4 | 5 | 4 | 4 | 2 | 5 | 4 | 4 | 50 | Singh, Navwinder | 1 | 100% | 80 | 80
54390586 | Singh, Ravinder | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 3 | 5 | 3 | 4 | 4 | 50 | Singh, Ravinder | 1 | 100% | 80 | 80
54387730 | Pang, TSZ HO | 1 | 3 | 4 | 3 | 3 | 5 | 3 | 4 | 5 | 6 | 4 | 5 | 4 | 50 | Pang, TSZ HO | 1 | 100% | 80 | 80
54387858 | Bilo, Mathew | 1 | 4 | 4 | 3 | 4 | 4 | 4 | 5 | 6 | 4 | 2 | 5 | 4 | 50 | Bilo, Mathew | 1 | 100% | 80 | 80
| Total Effort | 7 | 18 | 20 | 21 | 18 | 20 | 19 | 22 | 22 | 23 | 19 | 21 | 20 | 250 | Max | 1 |  | Average | 80
[19 empty] | Max | 80
[19 empty] | Min | 80

## Weekly Activity Log
Week | Weekly Activity Log | Completed By
Week 1 | Recruit Project Memebers to Form a Team + Team Building Exercises (Icebreaking) | Dheeraj Khurana + Navwinder Singh
Week 2 | Research on possible topics and selecting a suitable one with the concensus of entire team | All Team
Week 3 | Brainstorming on the Smart Trading Platform topic and deciding on the possible functional and non-functional requirements. | All Team
Week 4 | Finalising on the outline of the project and making the use case Diagrams, class diagrams, sequence diagrams. | All Team
Week 5 | Working on the main backend computation (Primary focus on computation =>Higher Scope for testing) | All Team
Week 6 | Testing is being intiated. Also, different design patterns are highlighted in the bakcend computation code. | All Team
Week 7 | Test Cases are made with a bottom up approach in mind on different classes. | All Team
Week 8 | Unit Testing is in progress. Control -flow and Predicate style testing is under going. | All Team
Week 9 | Integration testing is on going on the Maverick- The Smart Trading Platform. | All Team
Week 10 | System testing is initated. Bug reports are being create using Bugzilla. | All Team
Week 11 | Completion of system testing. Shift of focus on completing bug reports and code refraction. | All Team
Week 12 | Code Refracting takes place with the objective of improving the complete backend computation design. | All Team
Week 13 | Focus on preparing different report, installation guides and user manual for final users. | All Team
Week 14 | After suggestions/feedback from the professor during the presentation week some more changes related to computation and test cases were incorporated. | All Team